COMPREHENSIVE INTEGRATED MANAGEMENT PLAN

FOR THE MAYAGÜEZ BAY WATERSHED

RESEARCH PROGRAM

## Quarterly Progress Report

Date of Report: 6 June, 2002		For Quarter Ending:   31 May, 2004

(nov/31, feb/28, may/31, aug/31)

Project No. CIMP-002

Project Title: Nutrient discharges from Mayagüez Bay Watershed __________

PI’s name: David Sotomayor Ramírez 	Telephone: 787-265-3851 x3734 	Fax: 787-265-0860 email: david_sotomayor@cca.uprm.edu

Project Status: _x_   On Schedule	__Suspended	__Delayed	__Cancelled 	__ Completed

Percentage of Work Completed: __75% (year)_____ Completion Deadline: 31 August, 2002_____

The applicant is requesting that an extension be granted for this CIMP project through ____/____/____.

(Please attach project extension justification.)

Activities progress:  (According to Work Schedule submitted with application)

| Task # | Major Activity | Date Started | Estimated Date of Completion | Date Completed | % Complete | Dependant on Task(s): |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Surface Water Resources and Geographical Information System | 9/01 | 6/04 |  | 95 |  |
| 2 | Nutrient, sediment, and bacterial quantification (base flow) | 5/02 | 12/03 |  | 95 |  |
| 3 | Nutrient, sediment, and bacterial quantification (storm events) | 8/03 | 6/04 |  | 75 |  |
| 4 | Analysis and interpretation of water quality data (relate trends in water-quality parameters to land use, hydrologic discharge, point and non-point sources) | 1/03 | 7/04 |  | 50 | 1,2,3 |
| 5 | Quantify nutrient (total N, total P, DRP) export coefficients from watersheds | 1/03 | 7/04 |  | 95 | 1,2,3,4 |
| 6 | Apply a model of an indicator of actual P transport (the P index developed by USDA-NRCS) to selected farms within the subwatersheds | 1/04 | 7/04 |  | 50 |  |

Summary of Progress on Project this Quarter:  See attached report after this sheet.

(Attach additional sheet, if necessary)

I request that the attached file be included as progress report for the Quarter corresponding to May 2004 (CLCS_Watershed.pdf).  This presentation will be presented in “XVI Congreso Latinoamericano de la Ciencia del Suelo” in Cartagena Colombia, September 2004.

Problems Encountered and/or Assistance Needed:

(Attach additional sheet, if necessary)

As principal investigator, I request that the project corresponding to this report receive a no-cost extension through 31 December 2004.  The funds remaining in the project will be used to pay for the assistantship of a graduate student that will finalize his Master’s Thesis in Semester 1 of Academic year 2004-2005.

Thank you,

Certification:

As the Principal Investigator, I certify that the information contained within this quarterly report accurately reflects the status of this CIMP project.

___________________________________________________________________________________

Principal Investigator Signature & Title							Date

# CIMP Project Authorized Representative Use Only

Funding Status:    ___ Unchanged     ___ Overruns   ___ Underruns

Funds Expended to Date $______________ Anticipated Cost Overruns/Underruns: $_____________

Payment Request this Quarter: $_______________ Payment Received this Quarter: $_____________

Project Extension Authorization:

Based upon our review of the supporting documentation, the requested project extension is justified. The project director authorize an extension of this project through _____/_____/_____.

_____________________________________________________________

Director’s Signature						Date